## Slide 1: Filter Exchange System Status Pierre Karst Filter Exchange System Manager – IN2P3 3 Octobre 2019

## Slide 2: L’équipe CPPM
Chef de Projet Echanger de Filtre
P. Karst

## Slide 3: Auto Changer progress in 2018-2019
Prototype unit : Fully assembled and tested (Stand-alone test, cold test, combined tests)
Final unit 1:
  The Assembly and the Stand-alone tests are complete
  The Combined Test with the Filter Loader and the Carousel is complete
  The test at cold and warm Temperature is done (-17°C ; 35°C)
Final unit 2 :
  Fabrication in progress : Expected end of June 2020 (Not fully funded in 2019)
  Assembly and Stand Alone Test : Spring and Summer 2020
  Combined Test : Fall 2020
  Delivery : End of 2020, early 2021
Auto Changer on the Transport Clean Box
Auto Changer on Stan-alone Test Bench
Auto Changer on Stan-alone Test Bench

## Slide 4: Verification and Validation activities status
Test Loader/Auto Changer :
  The alignment of the Loader with the Auto Changer is done.
  The Filter Hand-off is verified and validated.
Combined Test :
  All the system has been mechanically tested with 5 filters on the carousel (Filter Loading and Filter Hand-off) => June and July 2019
  Tuning of the control/command done on August and September 2019
  Many travels at Paris
Shipment to US (SLAC) : Early October
  BackFlange + Carousel : Plane => End of Novembre
  All the System : Boat => Early December
  Operations at SLAC :
    Unpacking and test : December 2019
    Camera Integration : February 2020
Combined Test Auto Changer/Filter Loader
Loader
Auto Changer
Dummy Camera Body
Auto Changer
Carousel
Auto Changer and Carousel on the Test Bench