## Slide 1: Conclusions of Task 4.3 meeting Dec 16-17, 2019
Mark ALLEN
CDS, Observatoire de Strasbourg

## Slide 2
Next steps:
Tech Forum
- Presentation on Task 4.3 on progress and ideas.
Hackathon meeting – demo in Jupyter notebook? (2 hrs)
Cross-WP4/5 question – desired platform capabilities from Task 4.3 experience
Task 4.3 Meeting
End March/ beginning April 2020 – Strasbourg (date TBD)
Make plans for imaging, catalogue, cube explorations.
Input for ESCAPE progress meeting - 3 slides (to be finalized at Strasbourg Tech forum)
( - input for ESO users committee: 2-3 slides for April 2020) – MR to decide
Input for mid-term report. Written description of progress: probably needed by end June 2020
- Meeting HITS before summer 2020 (probably July)
(how do we keep that after finished? - who can re-run it?) (F-X - visit to HITS)
- AD’I Jan-June 2020: Concentrate on UVES data, apply same approach as done from HARPS, but also look for overlaps. (Make the prototype system somehow transferrable)
- Toward the Deliverable Demo - July 2021
- A vision for the demo; February 2021
- Define venue/audience for demo: ESO Users committee 2021, EWASS 2021, IAU 2021?

## Slide 3
Spectra: * finalize HARPS - atmosphere removal (short investigation by HITS before Tech forum). Try the system with simulated stellar spectra - is similar really similar? ESO (John) – goal to show in April 2020 (may involve pre-procesing/norms/...?) * UVES work - Self-Organizing-Maps? - What to do instead of 0-padding? - Does the dimensionality reduction cluster different "objects" (galaxy, star, QSO, BD) ? - Getting labels from SIMBAD and ‘re-label' centroids [FS(ESO) – CDS] - Question: are we good enough with redshifts? * Gather some initial feedback from astronomers: what is a "similarity" of spectra that *they* would find useful for *their* science -> maybe this will lead to different methods of pre-processing/loss-function * Precision topic:
  - How many dimensions do we need to capture "most" of the spectral information ? - ESO to try to force orthogonality in latent space + order by importance - Noise estimation and then decide on the dimensions that are really necessary
  * Other instruments ? Consider which spectrographs addition to HARPS and UVES - can we make one model that can contain spectra from all/more instruments?

## Slide 4
Interface:
* Think of concepts for the interfaces