## Slide 1: Work Package Six: «ECO» Engagement and Communication
Stephen Serjeant, Open University WP6 Lead
Rita Meneses, Trust-IT Services
Mathilde Hubert CNRs-LAPP
ESCAPE All-Hands Meeting, 26° February 2020

## Slide 2: Vision
ESCAPE science community
Society at large
Task 6.1
Mass Participation Experiments
Task 6.2

## Slide 3: WP6 - Engagement and Communication
Timing: M1-M48;
Lead: Trust-IT Services (28PM)
Partners Involved: CNRS-LAPP (12PM) & OU (2PM)
Deliverables:
  D6.1 – ESCAPE website live (June19)
  D6.2 – Dissemination & Exploitation Plan (Janry20)
  D6.3 – Brochure publication (June20)
Contributions requested within the next 6 months:
  Blogposts from EOSC WG members
  Each 2 months, a WP updated about latest activities
  Pieces of news / Webinars of ESCAPE Services & Science projects
Synchronyse our efforts of communication by liaising well with all WPs to ensure that a consistent message is carried out throughout the whole project timeframe
“Task 6.1 Public Engagement and Communication”
T6.1 Leader

## Slide 4: Timeline of activities done in M1-M12 Feb 2019 – Jan 2020
WP6
M1
Branding, rollup & templates
KoM Annecy
Flyer
M5
Social Media networks
M7
Website revamp
M9
M12
EOSC Jam Session -IT
Interviews
M3
M6
M8
M10
Services branding
D6.1 – ESCAPE project website live
D6.2 - Dissemination and
exploitation plan
Website live
2 posters
1 poster
1 position statement
1st Press Release
1st CS project
New Section: organisation
EWAAS -FR
Astronomical Data Archives Meeting - AU
Open Talks at Open University- UK
IBERGRID - ES
ADASS - NL
Building EOSC - BE
ECFA-NuPECC
-ApPEC - FR
RDA Plenary - FI
CHEP2019 - AU
ESA/ESO SCIOPS - ES
EOSC Symposium - HU
REINFORCE KoM - IT
Communication & engagement activities in Y1, to support a successful exploitation
WP5 workshop on Science Platform design and requirements - NL
Workshop: Data Infrastructure and Analysis Platform: defining architecture and implementation plan - NL

## Slide 6: WP6 - Engagement and Communication
Task 6.1 Public Engagement and Communication” goals
  Develop ESCAPE website & portal tailored to different stakeholders & the gateway for the catalogue of services
  Share with us relevant updates from your WP
Generate ESCAPE Communication Toolbox (PR, flyers, posters, videos, stands).
  To use at events at exhibitions when engaging with stakeholders
Support attendance at external high-level events and meetings.
  Get our support on online visibility through social media channels | Fill in the “excel” to track events’ presence.
Communication & Community User Engagement are continuous tasks, to engage directly with stakeholders with content rich insights
Establish a dissemination and exploitation plan: KPI definition & monitoring: D6.2 – Dissemination & Exploitation Plan
Disseminate internally ESCAPE results, within the community and beyond.
  We are all ESCAPE’s ambassadors
Co-ordinate translation and adaption of resources for different national communities & compile master Classes and MPE online resources (EN, DE, ES, FR & IT)
Support ESCAPE final Event to showcase the final results of the ESCAPE project
T6.1

## Slide 7: Communication Strategy in ESCAPE
WP6
Network stakeholders from different backgrounds
Outreach to distinct audiences & future end-users about ESCAPE future developments
Highlight real use-case scenarios between ESCAPE and Science Projects
Promote interdisciplinary synergies to unlock potential for discovery, to support the implementation of EOSC thanks to open data management
W
H
A
T
W
H
Y
HOW
Identify stakeholders & engage with them using adequate communication tools & channels. Create communication pieces to spread the word & raise awareness
Focus on the end-users & obtain testimonials from them
YEAR 1
CREATE AWARENESS ABOUT ESCAPE
Increase stakeholders’ engagement to stimulate adoption of ESCAPE results
YEAR 2
SERVICE FEEDBACK & TESTING
Collect feedback & perform tests with future service users (science projects), to ensure service adoption & sustainability for the long-term. Contribute to EOSC discussions
Workshops & schools, perform assessments, develop initial pilots and test science projects, publish stories from science projects to demonstrate service value propositions & engage directly with stakeholders.
YEAR 3
SERVICE PROMOTION & DEPLOYMENT IN EOSC
Deliver the “Astronomy and Particle/Nuclear Physics EOSC cell”, following FAIR principles
Promote the ESCAPE EOSC cell across sectors, organise workshops for service final training, consolidate synergies with EOSC & leverage with international initiatives/player
Services
Science Projects

## Slide 8: Editorial Plan – What is next?
T6.1
Ensure both ESCAPE’s website & social media channels require continuous & timely dissemination of each WP developments, to effective engagement with each stakeholder group
User-stories: ESCAPE services vs each Test Science Project (TSP)
  Interviews and/or news articles with testimonials
  Webinars to showcase first collaboration results from ESCAPE vs research infrastructures
  Max 30-second videos for each TSP
ESCAPE WPs updates: bi-monthly WPs updates on the website
  Each month to have 1 dedicated news piece from 3 ESCAPE WPs
ESCAPE Services: publish dedicated news of each ESCAPE service
  ESCAPE OSSR news article is online
ESCAPE & EOSC: ESCAPE contribution to EOSC
  Video
  Blogposts from members part of the EOSC WGs.
  News articles about ESCAPE in FAIRsFAIR EGFC
Deliverables: concise news piece about the
purpose, results, end-user benefits and conclusion
Others: presence at 3rd party events & ESCAPE workshops
Testimonials from end-users

## Slide 9: Branding & Comm material
T6.1
Flyers
Flyer 1
D6.3 completed in M5
Poster 1, Poster 2 – ADASS Conference, M9
Communication Channels & Materials to set the basis for stakeholders’ engagement
Flyer 2 – M13
Press Release – M1
Rollup Banners:
M1 & M13
PROJECT LOGO & PPT / WORD TEMPLATES
Rebranded logos by M13
Available in the Comm-kit area of the website
By M12 & M13
VIDEOS
3 Videos – Month 4, Other Videos to be produced
PRINTED MATERIALS
Poster 3 –EOSC Symposium M10
DIGITAL MATERIALS
POSTERS
ROLLUP BANNERS
FLYERS
PRESS RELEASE
5 SERVICE LOGOS (+ 2 REBRANDED)
INFOGRAPHICS & SOCIAL MEDIA IMAGES

## Slide 10: Branding & Communications material
T6.1

## Slide 11: Branding & Communications material
T6.1

## Slide 12: Branding & Communications material
T6.1

## Slide 13: Website Evolution
T6.1
Website continuous improvements to better disseminate ESCAPE’s results
Website 1° Version – M5
Website 2° Version – M8
New URL: projectescape.eu
New sections:
  Services, Science Projects, News, Events, Deliverables and Presentations, About us,
  Access Internal Tools for Partners;
UPDATES SINCE WEBSITE LAUNCH
Included Newsletter subscription form
New website search box
Revamped sections: Comm-Kit, Citizen Science Page and Organisation Section
  Waiting for WP1 & WP4 info for the website
Submission of “D6.1 – ESCAPE Website live” by M8
RESULTS BY JANUARY 2020
Nº Visitors  2.351
Page Views  13.910 (Jan 2020)
The exploitation plan after ESCAPE conclusion?
Online catalogue of ESCAPE services
What else?

## Slide 14: Website Evolution
T6.1

## Slide 15: Website Evolution
.
T6.1

## Slide 16: Social media Channels
T6.1

## Slide 17: Social media Channels
T6.1

## Slide 18: Visibility at events
T6.1
Total of 15 events, reaching different stakeholders
August 2019
Sydney, Autralia
Astronomers & Data Managers
September 2019
Compostela, Spain
Software developers, data managers & computing professionals
October 2019
Groningen, The Netherlands
Astronomers Data Analysis & Software Systems
Astronomy, astroparticle, particle & nuclear physics events
Other events
June 2019
Lyon, France
Astrophysicists
Astronomical Data Archives
IBERGRID
2nd IVOA - ADASS
September 2019
Online event
Students
& general public
Open talks at Open University
EOSC related events
November 2018
Austria
Research Communities
& Policy Makers
January 2019
London,UK
ESFRI & EOSC stakeholders
June 2019
Turin, Italie
EOSC & Clusters projects
ESFRI RIs
& EOSC Workshop
EOSC related projects
October 2019
Helsinki, Finland
EOSC & Research Data Communities
November 2019
EOSC Communities, Research, Industries, Policy Makers
EOSC Symposium
EOSC Services, Collaborations
& the RDA
Building EOSC through the H2020 projects
September 2019
Brussels, Belgium
December 2019
Pisa, Italy
Academia
& citizen science professionals
Reinforce kick-off meeting
October 2019
Orsay, France
Data science and astroparticle physics professionals
November 2019
Adelaide, Australia
Computing professionals from High Energy and Nuclear Physics.
November
Madrid, Spain
ESA and ESO communities concerned with “cross-facility coordination in the multi-messenger era”
Joint ECFA-NuPECC-ApPEC Data Archives
24th Conference
on Computing
in High-Energy
& Nuclear Physics
ESA/ESO SCIOPS workshop

## Slide 19: Vision
ESCAPE science community
Society at large
Task 6.1
Mass Participation Experiments
Task 6.2

## Slide 20: T6.2 Timeline of Actions & Outlook for M1-M48
e-eco@escape2020.eu
M1
M0
Branding & Identity
KoM Annecy
Recruit ML/CS PDRA
M5
D6.4: Citizen Science experiments & education
M24
M36
M48
Two hands-on workshops to generate projects for D6.4 and D6.6
D6.6: Citizen Science experiments & education
Final Event
D6.5: Promotional videos
M41

## Slide 25
STOP PRESS:
LAUNCHED TUE 25 FEB

## Slide 27: T6.2 Timeline of Actions & Outlook for M1-M48
e-eco@escape2020.eu
M1
M0
Branding & Identity
KoM Annecy
Recruit ML/CS PDRA
M5
D6.4: Citizen Science experiments & education
M24
M36
M48
Two hands-on workshops to generate projects for D6.4 and D6.6
D6.6: Citizen Science experiments & education
Final Event
D6.5: Promotional videos
M41

## Slide 28: T6.2 Timeline of Actions & Outlook for M1-M48
e-eco@escape2020.eu
M1
M0
Branding & Identity
KoM Annecy
Recruit ML/CS PDRA
M5
D6.4: Citizen Science experiments & education
M24
M36
M48
HANDS-ON ZOONIVERSE WORKSHOP IN JULY 2020 – DETAILS SOON AND TASTER TODAY!
D6.6: Citizen Science experiments & education
Final Event
D6.5: Promotional videos
M41

## Slide 29: Thank you very much!
Stephen Serjeant: stephen.serjeant@open.ac.uk
Rita Meneses: r.meneses@trust-itservices.com
Mathilde Hubert: hubert@lapp.in2p3.fr
@ESCAPE_EU
linkedin.com/company/projectescape/
youtube.com/channel/UC05braEQdP2rCSUamHm9I_Q
Follow ESCAPE on