## Slide 1: STRONG-2020: Project Review 28 September 2022 COVID -19 impact on the Project

## Slide 2: COVID -19 impact
Activity of most of Transnational Access Infrastructures was severely limited. Consequently, many TAs could deliver only a limited amount of access,
especially in the first Reporting Period
Several WPs have been affected
realization of certain tasks was delayed
resulted in the delay of submission for a number of deliverables and in the achievement
of some milestones
The accumulated delays led to the request of a six-months extension of the project (accepted with the second Amendment)

## Slide 3
1) TA2: Transnational Access to MAMI
Min. quantity of access to be provided in Annex I (Unit of access: Beam hour): 1 750
Access provided in RP1: 178
Access provided in RP2: 152
Difference (to be provided): 1 420
2) TA3: Transnational Access to LNF
Min. quantity of access to be provided in Annex I (Unit of access: Beam hour): 2 500
Access provided in RP1: 820
Access provided in RP2: 1 170
Difference (to be provided): 510
COVID -19 impact: TAs

## Slide 4
3) TA4: Transnational Access to FTD/ELSA
Min. quantity of access to be provided in Annex I (Unit of access: 1 AU) : 1 400
Access provided in RP1: 0
Access provided in RP2: 677
Difference (to be provided): 723
4) TA5: Transnational Access to GSI
Min. quantity of access to be provided in Annex I (Unit of access: Beam hour): 1 450
Access provided in RP1: 0
Access provided in RP2: 860
Difference (to be provided): 590
COVID -19 impact: TAs

## Slide 5
5) TA6: Transnational Access to ECT*
Min. quantity of access to be provided in Annex I (Unit of access: Access-day): 1 900
Access provided in RP1: 253
Access provided in RP2: 611
Difference (to be provided): 1 036
6) TA7: Transnational Access to CERN
Min. quantity of access to be provided in Annex I (Unit of access: 1h): 3 000
Access provided in RP1: 235
Access provided in RP2: 672
Difference (to be provided): 2 093
COVID -19 impact: TAs

## Slide 6
Inaccessibility or very limited access to Transnational Infrastructures had as a consequence:
TAs of the project could not fulfill their tasks and provide the amount of access foreseen in the GA
several JRA and NA members were unable to access the facilities necessary for the tasks described in the GA
Postponement of a number of Deliverables as a result of COVID-19 restrictions
Rescheduling of the due dates for a number of milestones
Impossibility of organizing in-person meetings and exchange of experience
especially important for NAs but also JRAs
Deviations in the use of budget (more Personnel costs spending and very limited Travel costs use)
Human effort revisions and budget transfers for a number of WPs following Work Plan modifications
Consequences for the project

## Slide 7: Perspectives
Possibility of a second extension:
Arguments for:
For TAs: carry out the work plan and fulfill the obligations set out in the GA
For VAs: ensure the follow-up and maintenance of services/databases created during the project
Other WPs: some WP leaders have expressed their desire to have another extension to finish delayed (due to COVID-19) tasks
For the whole Consortium: maintain the network in the perspective of the construction of a project corresponding better to the new directives/priorities of Horizon Europe
Potential difficulties:
Accomplishment of tasks for some WPs less impacted by the pandemic (budget expended)
Discussions with WP leaders is planned for the Annual Meeting on 18-19 October

## Slide 8
We thank you for your attention