## Slide 1
WP2 – Communication, Dissemination and Exploitation / Integrating Activities

## Slide 2: WP2 Objectives
Set up and maintain multiple communication channels to ensure the visibility and outreach of the project activities among national and international audiences.
Disseminate and communicate the project outputs and knowledge generated towards the scientific and industry communities in a timely and consistent manner and in line with Open Science practices.
Explore possibilities for the exploitation of the results with stakeholders to ensure uptake of project outputs.
Maximize the impact of the project by participating in various events attended by key stakeholders.

## Slide 3: WP2 Tasks
TASKS | TASKS |  | LEAD | CONTRIBUTION
2.1 | Communication | Project website | ESF | All partners
 |  | Newsletters, social media, press-releases |  | 
 |  | Promotional material (leaflets, banners, posters) |  | 
 |  | Visual Identity (logo, templates) |  | 
2.2 | Stakeholders Mapping and Engagement | Stakeholder analysis and mapping | ESF | All partners
 |  | Coordination with relevant EC-funded projects and organisations, and integrate with EC-roadmaps |  | 
2.3 | Dissemination | Scientific papers & conference proceedings | ESF | All partners
 |  | Project booth at relevant events |  | 
2.4 | Public Engagement | Outreach events in coordination with partner facilities to raise awareness about the project and engage local stakeholders | ESF | Partner facilities
2.5 | Exploitation of project results | Project conference with stakeholders leading to co-creation of a roadmap on exploitation opportunities and uptake of the project outputs | ESF | All partners
2.6 | Data Management and Intellectual Property | Data Management Plan to outline how data is processed and protected during the project | ??? | All partners

## Slide 4: Task 2.1 Communication
ESF, ESS, UM, all partners
Project website
Social media channels (X or other platforms, linkedin, youtube, etc.)
Visual identity: logo, guidelines, templates (presentations, reports, deliverables, etc.)
Newsletters, communication materials, make use of existing communication channels (CERN newsletter, etc.)
Press-releases and policy briefs
⚑ Milestone Project website, visual identity and communication channels set up by M3
☑ Deliverable D5.1: first Dissemination, Exploitation and Communication plan developed by M6 (updated in M9, M12, M24 and M36)

## Slide 5
Activities | Key Performance Indicator (KPI) | KPI Target
Communication | Number of visits on the website | 250 per month
 | Search engine position | First page
 | Number of posts on social media | 100+ posts per year
 | Number of followers across all social media channels | 1000+ altogether
 | Number of subscriptions to the newsletter | 200+
 | Number of promotional videos produced | At least 3
 | Number of policy briefs produced | At least 2
 | Number of press releases | At least 4
Dissemination | Number of open access publications in high impact scientific journals | 15+
 | Number of participations in scientific conferences | 15+
 | Number of participants at local exhibitions | 50+
 | Number of industrial events attended (booth) | 2+
 | Number of local events in schools and universities (all partners) | 10+
Exploitation | Number of training materials produced | 16 (2 per key result)
 | Number of participants at ARTIFACT conference | 100+

## Slide 6: Task 2.2 Stakeholders Mapping and Engagement
ESF, ESRF, all partners
Identification of relevant stakeholders
Integrate project with relevant EC-roadmaps
Clustering activities with accelerator and detector facilities as well as with relevant EC-funded projects and organisations
Engagement with stakeholders monitored with quantitative and qualitative indicators of engagement
☑ Deliverable Key European stakeholders are identified by M9 (update of the Dissemination, Exploitation and Communication plan)
☑ Deliverable D5.2 Report on stakeholder engagement, communication and dissemination activities (M48)

## Slide 7
Stakeholder Group | Stakeholder Name

## Slide 8: Task 2.3 Dissemination
ESF, all partners
Publication of all scientific papers resulting from the project in open access
Presentation of research outcomes in relevant scientific conferences
Project booth is held at relevant events attended by stakeholders
Promotion of project in local scientific events, schools and university
Other ideas?
☑ Deliverable D5.1: first Dissemination, Exploitation and Communication plan developed by M6 (updated in M9, M12, M24 and M36)

## Slide 9: Task 2.4 Public Engagement Events
ESF, ESS, partner facilities
Outreach events in coordination with partner facilities open days or scientific outreach platforms (e.g. CERN scientific gateway, other?)
Involvement of local stakeholders from industry, governmental organisations, etc
Raise awareness about the project and engage local stakeholders about other potential local applications of the project outputs
⚑ Milestone Public Engagement Events from MX onwards

## Slide 10: Task 2.5 Exploitation of project outputs
ESF, all partners
Organization of the project conference with key stakeholders to present the project outputs and explore the possibilities for their exploitation beyond the lifetime of the project.
Co-creation of a roadmap on exploitation opportunities and uptake of the project outputs with the involved stakeholders
Training webinars and handbooks on the exploitation of the project outputs with project partners?
Other ideas?
⚑ Milestone Project conference organized around M38
☑ Deliverable D5.3: Roadmap on exploitation opportunities published on M48

## Slide 11
Key Exploitable Result | Potential users | Partners to exploit | Routes to exploitation | IPR strategy | TRL (start) | TRL (end)

## Slide 12: Task 2.6 Data Management and Intellectual Property?
Lead???, all partners
Outlines how data is processed and protected during the project under the FAIR principles and in compliance with Open Access policy.
Defines standards to be adopted, how the data are shared, ensuring that IP rights and all regulations, rules and laws, related to data, are respected.
Measures to ensure IP protection are outlined in the consortium agreement.
☑ Deliverable D5.4 first Data Management Plan by M6 (updated in M21 and M42)

## Slide 13: Deliverables
D2.1 Dissemination, Exploitation and Communication plan (Lead: ESF, M6) First draft of the ARTIFACT communication, dissemination and exploitation strategy, including stakeholders' analysis and mapping, identification of key messages and outreach methodology. This plan is updated on M9, M12, M24 and M36.
D2.2 Report on stakeholder engagement, communication and dissemination activities (Lead: ESF, M42) Report on actions taken to engage different stakeholders and related outcomes, including social media activities conducted in the frame of the project, together with quantitative and qualitative indicators of engagement.
D2.3 Roadmap on exploitation opportunities (Lead: ESF, M42)
D2.4 Data Management Plan (Lead: ???, M6)