Name of the project:

Table 3.1c:	List of Deliverables

Only include deliverables that you consider essential for effective project monitoring.

| Number | Deliverable name | Short description | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date (in months) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ILDG | Upload of first 2 PB of LDG gauge ensembles to ILDG 2.0 | 2 | UREG | DATA | PU | 13 |
| 2 | Computing | Benchmarking of Lattice QCD kernels on novel computing platforms | 2 | FZ Jülich | R | PU | 25 |
| 3 | White Paper | White Paper on lattice hadron physics | 2 | SDU Odense | R | PU | 37 |

KEY Deliverable numbers in order of delivery dates. Please use the numbering convention <WP number>.<number of deliverable within that WP>. For example, deliverable 4.2 would be the second deliverable from work package 4. Type: Use one of the following codes: R: Document, report (excluding the periodic and final reports) DEM: Demonstrator, pilot, prototype, plan designs DEC: Websites, patents filing, press & media actions, videos, etc. DATA: Data sets, microdata, etc. DMP: Data management plan ETHICS: Deliverables related to ethics issues. SECURITY: Deliverables related to security issues OTHER: Software, technical diagram, algorithms, models, etc. Dissemination level: Use one of the following codes: PU – Public, fully open, e.g. web (Deliverables flagged as public will be automatically published in CORDIS project’s page) SEN – Sensitive, limited under the conditions of the Grant Agreement Classified R-UE/EU-R – EU RESTRICTED under the Commission Decision No2015/444 Classified C-UE/EU-C – EU CONFIDENTIAL under the Commission Decision No2015/444 Classified S-UE/EU-S – EU SECRET under the Commission Decision No2015/444 Delivery date Measured in months from the project start date (month 1)

Table 3.1d:	List of milestones

| Milestone number | Milestone name | Related work package(s) | Due date (in month) | Means of verification |
| --- | --- | --- | --- | --- |
| 1 | Lattice Practices 2026 | 2 | 6 | Participant feedback questionaires |
| 2 | Workshop on multihadron dynamics in a box | 2 | 6 | Indico website |
| 3 | EuroLFT Town meeting 2027 | 2 | 13 | Indico website |
| 4 | Workshop on inverse problems in QCD and beyond | 2 | 18 | Indico website |
| 5 | EINN 2027 conference | 2 | 19 | Indico website |
| 6 | Workshop on precision low energy observables | 2 | 25 | Indico website |
| 7 | Lattice Practices 2028 | 2 | 30 | Participant feedback questionaires |
| 8 | EuroLFT Town meeting 2029 | 2 | 37 | Indico website |
| 9 | Workshop on heacy quark physics | 2 | 39 | Indico wbsite |
| 10 | EINN 2029 conference | 2 | 43 | Indico website |

KEY Due date Measured in months from the project start date (month 1) Means of verification Show how you will confirm that the milestone has been attained. Refer to indicators if appropriate. For example: a laboratory prototype that is ‘up and running’; software released and validated by a user group; field survey complete and data quality validated.

Table 3.1e:	Critical risks for implementation #@RSK-MGT-RM@#

| Description of risk (indicate level of (i) likelihood, and (ii) severity: Low/Medium/High) | Work package(s) involved | Proposed risk-mitigation measures |
| --- | --- | --- |
| Meetings, schools, workshops may be affected bu a pandemic: (I) risk: low (ii) severity: high | 2 | Move to online formats. |

Definition critical risk: A critical risk is a plausible event or issue that could have a high adverse impact on the ability of the project to achieve its objectives. Level of likelihood to occur: Low/medium/high The likelihood is the estimated probability that the risk will materialise even after taking account of the mitigating measures put in place. Level of severity: Low/medium/high The relative seriousness of the risk and the significance of its effect.

You must include a data management plan (DMP) and a ‘plan for dissemination and exploitation including communication activities as  distinct deliverables within the first 6 months of the project.  The DMP will evolve during the lifetime of the project in order to present the status of the project's reflections on data management.  A template for such a plan is available in the Online Manual on the Funding & Tenders Portal.