**Name of the project: POLARIS**

**Table 3.1c: List of Deliverables[[1]](#footnote-1)**

Only include deliverables that you consider essential for effective project monitoring.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Number** | **Deliverable name** | **Short description** | **Work package number**  | **Short name of lead participant**  | **Type** | **Dissemination level** | **Delivery date****(in months)** |
|  | Materials Measurement Set | Complete measurement set of target materials at dilution temperature |  | UBO | R | Public | 48 |
|  | Bubbling Demonstrator | Continuously replenishing bubbling cell at Mainz |  | UOY | DEM | Public | 48 |
|  | HTS Measurement Set | Complete measurement set of HTS tubes in longitudinal field |  | UNIFE | R | Public  | 48 |

|  |
| --- |
| **KEY** Deliverable numbers in order of delivery dates. Please use the numbering convention <WP number>.<number of deliverable within that WP>. For example, deliverable 4.2 would be the second deliverable from work package 4.**Type:** Use one of the following codes: R: Document, report (excluding the periodic and final reports) DEM: Demonstrator, pilot, prototype, plan designs DEC: Websites, patents filing, press & media actions, videos, etc.DATA: Data sets, microdata, etc.DMP: Data management planETHICS: Deliverables related to ethics issues. SECURITY: Deliverables related to security issuesOTHER: Software, technical diagram, algorithms, models, etc.**Dissemination level:** Use one of the following codes: PU – Public, fully open, e.g. web (Deliverables flagged as public will be automatically published in CORDIS project’s page)SEN – Sensitive, limited under the conditions of the Grant Agreement Classified R-UE/EU-R – EU RESTRICTED under the Commission Decision No2015/444Classified C-UE/EU-C – EU CONFIDENTIAL under the Commission Decision No2015/444Classified S-UE/EU-S – EU SECRET under the Commission Decision No2015/444**Delivery date**Measured in months from the project start date (month 1) |

**Table 3.1d: List of milestones**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Milestone number** | **Milestone name** | **Related work package(s)** | **Due date (in month)** | **Means of verification** |
|  | Networking meeting in York |  | 18 | Meeting held |
|  | First measurement at 1K in Bochum |  | 24 | Polarization measurement of 1k material sample |
|  | First measurement of HTS in Bonn |  | 24 | Field measurement at cryogenic temperature |

|  |
| --- |
| **KEY****Due date**Measured in months from the project start date (month 1)**Means of verification** Show how you will confirm that the milestone has been attained. Refer to indicators if appropriate. For example: a laboratory prototype that is ‘up and running’; software released and validated by a user group; field survey complete and data quality validated. |

**Table 3.1e: Critical risks for implementation** #@RSK-MGT-RM@#

|  |  |  |
| --- | --- | --- |
| **Description of risk (indicate level of (i) likelihood, and (ii) severity: Low/Medium/High)** | **Work package(s) involved** | **Proposed risk-mitigation measures** |
| Inability to use Elsa as an irradiation source due to accelerator downtime. Likelihood: high, Severity: low |  | Use of pre-irradiated materials |
| Unexpected delays due to putting into place the safety assessments, approvals in handling parahydrogen flows in the experimental hall.Likelihood: low, Severity: medium |  | Project has direct collaboration of experimental hall lead at Mainz. Extensive experience with safe control of hydrogen in the experimental hall. Work has been seeded by testing of standard cells in the hall. |
| Failure of intended longitudinal magnet in Bonn.Likelihood: low, Severity: medium |  | Use of alternative (Saclay) magnet which would require modification of related testing equipment. |

|  |
| --- |
| **Definition critical risk:** A critical risk is a plausible event or issue that could have a high adverse impact on the ability of the project to achieve its objectives. **Level of likelihood to occur: Low/medium/high**The likelihood is the estimated probability that the risk will materialise even after taking account of the mitigating measures put in place.**Level of severity: Low/medium/high**The relative seriousness of the risk and the significance of its effect. |

1. You must include a data management plan (DMP) and a ‘plan for dissemination and exploitation including communication activities as distinct deliverables within the first 6 months of the project. The DMP will evolve during the lifetime of the project in order to present the status of the project's reflections on data management. A template for such a plan is available in the [Online Manual](https://ec.europa.eu/info/funding-tenders/opportunities/docs/2021-2027/common/guidance/om_en.pdf) on the Funding & Tenders Portal. [↑](#footnote-ref-1)