## Slide 1: Titan accelerator status report Y. MARIETTE

## Slide 2: Outlines
  Project presentation
  C/C presentation
  C/C Status
  Remaining work

## Slide 3: Project presentation
1

## Slide 4: Project objective
  Providing neutrons to industry
  Evolving a research accelerator named IPHI (3MeV, 100 mA) built 30 years ago into an industrial accelerator
  This accelerator must be designed for 30 years of operation
  The Titan project aims to have two thermal neutron sources. The first source is dedicated to neutronography :
  Beam parameters :
Target | Mercury target | Mars target
Energy | 3 MeV | 
Power | 50 kW | 
Frequency | 100 Hz | 
Pulse duration | 7 ms | 3 ms
Mean current | 24 mA | 55 mA
Sakyamuni, Bhumisparsa Mudra, Tibet, 14th-15th century
Bronze and copper
X Ray
Neutrons (Organic/ligthweight matter)
Wood
Dried flowers

## Slide 5: Location in CEA Saclay site
Titan - 126
DIS - 472
Main entrance

## Slide 6: The Titan accelerator
Mercury : Lithium Liquid Target
Neutronography room
Initial IPHI accelerator space
50kW of protons at 3MeV
RF source (SSA)
Mars : Beryllium target
Notes: Solid State amplifier

## Slide 7: Synoptic of the accelerator processes
Mercury : Lithium Liquid Target test
Mars :Beryllium target
Titan accelerator has :
36 magnets
39 diagnostics (13 types)
> 370 Components for the Vaccum
> 29 vaccum chambers
…

## Slide 8: Planning
2026
2027
2028
  The project started in 2019 with the study phase
  Since 2021, we have been in the process of building the accelerator and, in parallel, we have manufactured the prototype of the lithium liquid target and carried out tests on this target (T4-2024)
  Next milestones :
T1-2029
Start of operations
T2-2027
Start of proton commissioning
T4-2027
End of proton commissioning
T4-2028
End of neutron commissioning
Continue the realization and installation phase
Notes: Thermal neutron flux x2 compared to simulations !
Maintenance periods are impossible because of the target activation

## Slide 9: Control-command presentation
2

## Slide 10: WP8 team : control-command
Electrotechnical Studies and Projects
Coordination
Operational Technology
Information Technology
FPGA technology
Automation
CDD
Sécurité informatique
Idriss BEN OUNAIES
Approximately 30 people involved in the DIS (not full-time)
Homemade !
Few subcontractors

## Slide 11: control and command framework
  Equipment standardization :
    Triggers and timestamping electronics : MRF, Meinberg
    Slow acquisitions : Siemens, Beckhoff, JMConcept, KISS
    Fast acquisitions : NAT, IOxOS, D-tAcq
    Server and switches : DELL, HP
  SCADA : EPICS
72 cabinets
600 control channels for the Machine Protection System
2200 control channels for diagnostics
800 alarms for the vacuum
10 servers
6 industrial PC, 9 MTCA rack, 10 PLC, 150 Beckhoff modules
1600 cables, approximately 66 km long, and 400 network cables

## Slide 12: technical choices and guidance for Titan and the lab
  New EPICS development environment : EPNix
  Using the Nix package manager to package and deploy EPICS servers and clients, as well as operating systems, on virtual machines and equipments
  Communication with PLC and many devices with OPC-UA
  VM managed with Proxmox and cluster clone for redundancy
  2 cabinets (with most C/C equipments) are dedicated for development and test before deployment in production
  Alarm web manager :
Workshop on Friday

## Slide 13: New domains in the lab
  Cybersecurity studies and certification
  VHDL development for FPGA gateware
  System and network administration
    Admin IT (cybersecurity, switchs configuration, active directory, services configuration, etc.)
    Admin OT (continous integration, proxmox admin, production software update, troobleshooting, assistance)
  Operations management
    Non-regression tests for critical systems
    Hardware management database with NetBox
    Documentation with Gitlab and Xwiki
    Source management and CI with Gitlab
    Issue management with GitLab
    Software and Hardware update

## Slide 14: C/C Status
3

## Slide 15: Electrotechnical status
  All the cabinets for the Vaccum have been completed
  All Diagnostic cabinets have been completed
  All MPS cabinets have been completed
  Servers and switches cabinets have been completed
  Cabinets for the proton source have been delivered
  Some cabinets for the power supply for magnets have been delivered
  The cooling, RF power supply and Personal Safety cabinets are subcontracted and under realization
~50 cabinets completed !

## Slide 16: Software status
  MPS is in progress
  MCS, OT and IT are in progress
  Many LCS are in progress : Diagnostics, power supply, Mars target
  Cybersecurity studies are in progress
  The C/C of the proton source was taken over by the team and tested
  LCS for the Vaccum is quite completed

## Slide 17: Remaining work
4

## Slide 18: Remaining work
  Power supply cabinets procurement
  Mercure target cabinets procurement
  Cabinets installation on site
  Install and connect the cabinets
  Finalize the software developments
  Deploy the software, configure the services and switches
  Tests and comissionning
Notes: Fenêtre entre installation et mise en service technique très courte : Il faut anticiper le max de tests

## Slide 19: Thanks for your attention