## Slide 1: IDS End 2 End Tests
French instrumental contribution status
Journées LISA France
04 May 2025
DAMERY JEAN-CHARLES (CNES)

## Slide 2: Agenda
01 – Context
02 – Progress
03 – Conclusion

## Slide 3
Context
01

## Slide 4: Instrument components
LISA Constellation
S/C 1
S/C 2
S/C 3
Instrument 1
Instrument 2
Telescope
Gravitational Reference Sensor (GRS)
Laser
Optical Bench
Phasemeter
OB Mechanism Control Unit
SDS
End 2 end tests @ CNES
Full performance testing based on:
  Engineering Model (EM)
  Qualification Model (QM)
OMS @ ESA

## Slide 5: LISA Payload CFI

## Slide 6: Device under test
The Decive under test for the E2ET system is composed of the following elements:
  OBA: Optical Bench Assembly
    Containts the interferometers, photoreceivers, Fiber injectors and beam alignment mechanisms
    Zerodur baseplate of 45 cm Ø
  PMS: Phase Measurement System
    Read-out electronics, DAC, DPLLs, Laser control logic
    Two electronic units (PMS-IPU & PMS-PCU)
  OBMCU
    C&C of the mechanisms in the OBA
    One electronic box
  Laser Tx
  Harnesses
PMS-IPU
PMS-PCU
OBA
Harness
OBMCU
Laser Tx EDU

## Slide 7: Environment silmulation
Simulation du second instrument
Simulation du satellite distant
TM
Environnement :
-Vide
-Thermique
-Propreté
-EMC

## Slide 8: E2ET setup composition

## Slide 9: Facility
“Signe3” Clean room at CST (Centre Spatial de Toulouse, CNES) dedicated to host the IDS E2E Test setup
  ~125 m² ISO8 room space
  Vacuum chambers
  CMM
    Capable of holding all the elements on the STS
  ISO5 capability
    Blowing Wall
  Utility room
  GSE room
  Control Room (outside controlled space
Electronics Vacuum Chamber
Optical Vacuum Chamber
CMM
Control Room
Blowing Wall
Utility Room
EGSE racks

## Slide 10: ESA challenges in 2026

## Slide 11
Progress
02

## Slide 12: E2ET Test setup development
  E2ET test setup reaching overall CDR level
  Most critical subsystems have reached or are close to reach CDR completion
  System level E2ET CDR expected Q1 2027
2023
2024
2025
2026
E2ET System level
Subsystem level
PDR
PDR
CDR
CDR
E2ET V-cycle
E2ET is here!

## Slide 13: E2ET V cycle development

## Slide 14: Current status in GSE development
Beams Simulator
System CDR started on April 1, should be closed on May 7
PhotoReceiver delta CDR scheduled on May 28
Manufacturing phase on going
Laser GSE
Integration on going
Tests at LTE of the STAB laser in June
Test Mass Simulator
Performance tests on going using the prototype
Manufacturing key point coming soon
STable Structure
Detailed design activities on going
CDR foreseen in June
Stray Light OGSE
ITT on going ; Proposal expected end of May
Thermal GSE
Passive thermal screen CDR done
Delivery expected mid 2026
PMS-GSE (with UHH)
Manufacturing phase on going
Delivery to APC of a first ADC board
Second milestone (over 3) of the contract done on April 29
TX Beam Dump
PDR closed
Detailed design o, going
Integration phase in CNES in 2026
TX Beam Dump
First version 1.0 of the GI EGSE in preparation
  Including TAU (L and K) and Pyramids (HW and SW)
Delivery expected in May

## Slide 15: E2ET Facility
  Facility elements are delivered and accepted:
    Clean room
    Vacuum Chambers
    Blowing wall (ISO 5 facility)
    CMM: Site acceptance
  Performance testing of the facility from 2Q2026 to 4Q2026. Including:
    Mechanical characterization: using seismometers and accelerometers. Microvibration levels on the ground and in the optical vacuum chamber
    Acoustic environment
    Thermal characterization: Thermal stability achieved inside the vacuum chambers, both with and without the passive thermal screen
    EMC characterization: Measurements of the radiative coupling between interior/exterior of the chambers, measurement of the CS on available units, test several grounding strategies.

## Slide 16: E2ET Schedule
      All GSE development schedules updated
      Update of the integration sequence done in conformance with the last integration sequence
        Nevertheless this integration sequence is still under construction / consolidation
IDS PDR status
Current status

## Slide 17: CNES team improvement in 2025

## Slide 18
Conclusion
03

## Slide 19: The machine is up and running
A solid and well-supported project that has demonstrated and continues to demonstrate a strong capacity for managing risks and changes (e.g., NASA)
Other risks and changes will probably come
A very rich retrospective since adoption (Q1 2024)
Even more work to be done
An instrumental contribution in the implementation phase, a characterization phase beginning, and integration, testing, and analysis phases to follow soon
A ground-based contribution in the early stages, but already showing initial results in terms of data, algorithms, and infrastructure software

## Slide 20
Thank you