## Slide 1: Status of the SPIRAL2-DESIR project
EAP DESIR
October 20, 2026, LP2i Bordeaux
J.-C. Thomas, GANIL, on behalf of the DESIR project management and collaboration
  - Project manager: Ch. Peaucelle, LPSC (09/14/2026)
  - Scientific coordinator and spokesperson: B. Blank, LP2iB
  - Facility manager: F. Varenne, GANIL
GANIL
SPIRAL2

## Slide 2: OUTLINE
DESIR
Introduction
Scientific program
Buildings
Transport beam lines
Beam preparation and purification
Timeline
Conclusion

## Slide 3
Introduction
DESIR

## Slide 4
EAP: DESIR@GANIL-SPIRAL2
CYREN
SPIRAL 1
SPIRAL 2
~30*50 m2

## Slide 5: DESIR: Experimental equipment
PIPERADE
(2028)
MR-TOF-MS
(2029)
GPIB
(2028)
MORA
(2029)
MLLTRAP
HINA
TORTILA
LRC
Decay station
(NA)2STARS
(2029)
Id.
Station
(2028)
COeCO
Installation and operation --> >2030
ARGOS
gSPEC
….
LUMIERE
BESTIOL
DETRAP
LINO-LASAGN
(2027)
……
……
……
P. Ascher
P. Delahaye
M. Fallot
E. Minaya Ramirez
5
L. Lalanne
G. Tocabens
S. Naimi
L. Canete
DESIR Project perimeter
M. Gerbaux
L. Hayen
bSTILED
WISArD
X. Fléchard
M. Versteegen

## Slide 6
Scientific program
DESIR

## Slide 7: Scientific program
Preparation of DESIR physics case
Workshop DESIR: Spring 2024:100 participants, 22 institutes (15 from foreign countries)
Workshop LUMIERE: July 2024
Workshop BESTIOL: Dec. 2024
Workshop DETRAP: May 2025
Brainstorming (IN2P3): Impact of high-precision measurements on BSM physics at DESIR, July 2026
Letters of intent
DESIR LOI workshop: March 2026, > 50 LOIs
-> Working group to analyze the feasibility (RIBs), propose RIB developments and experiment priorities
=> Commissioning and Day-1 exp. strategy: GANIL SC - B. Blank, Nov. 2026
-> DESIR collaboration Committee: detailed LoI
Proposals ≥ 2027
Equipment commissioning: 2028-2029
Stable and radioactive beam without going through proposals and PAC
Routine operation ≥ 2030
7

## Slide 8: Scientific program: DESIR LoIs - March 2026
Overview
50 LoIs, ~2000 UTs, ~300 isotopes from 6He to 263Sg, from 0.01 to 107 pps
90% from French labs (46% IJClab)
Mainly n-deficient (production sites)
Using different techniques to probe the same region (e.g. around 100Sn)
Combining different setups, e.g. PIPERADE + Decay spectroscopy
Combining S3-LEB and DESIR studies
Using beams expected from either S3-LEB (29 LoI) or SPIRAL1 (50 LoI) (overlap)
-> Feasibility to be checked: Day-1, Day-2, RIB devpt. priorities
Setups/Techniques
Physics cases
Labs
Chart: 
| IRFU | GANIL | LP2iB | IJCLab | LPCC | Subatech | IPNL | Spain | India | Turkey | Belgium
 | 1 | 6 | 9 | 23 | 2 | 2 | 1 | 2 | 2 | 1 | 1
Chart: 
| Nuclear structure | Astrophysics | Fundamental interactions | Exotic decays | Interdisciplinary
 | 32 | 7 | 7 | 3 | 1
Chart: 
| S3-LEB | BESTIOL | LUMIERE | DETRAP
 | 4 | 29 | 15 | 24
8

## Slide 9
Buildings and Infrastructure
DESIR

## Slide 10: Buildings and infrastructure
RFQ1P + HRS room
Experimental hall
Salle 301 : Hall d’expérience
Laser rooms
51.50m
31.35 m
Laser room
9.50 m
8 m
11.25m
Laser room
Building delivery: 11/2025
Building operation (internal licence): 01/2027
Facility operation (safety licence request)
About to be submitted
Expected green light: 10/2028?
10

## Slide 11
Transport beam lines
DESIR

## Slide 12: Overview: Transport beam lines
Base assembly
Insertion
Pole assembly
Internal part
Upper part
Example: 45° deflector assembly
SPIRAL1
DESIR Hall
Courtesy: V. Watt-Morel
Courtesy: L. Perrot
SP1 -> DESIR beam line
Junction beam lines from SPIRAL1 and S3-LEB to the DESIR Hall: ~100 m
1+ ions, < 60 keV, < 80 p.mm.mrad – fully electrostatic
Courtesy: Ph. Alfaurt, L. Daudin
Test bench
3 keV
Level -1
-3.25 m
Level -1
-3.25 m
Level -3
-9.5 m

## Slide 13: Transport beam lines: Prototype section
Validation of:
Assembly protocols √
Vacuum tests √
Cabling principles
Supplies integration √
Diagnostics insertion √
PLCs
Interlocks
Beam tuning software
SPIRAL1 -> --------------------------(~20 m)------------------------------ DESIR
Still a lot to do: e.g., cabling
-> offline commissioning in 2027

## Slide 14: Transport beam lines: Junction tunnels
Installation of the beam line equipment (mechanics/optics): Early 2026 ---->
Call for tender for the cabling and piping: October 2026
GANIL Cyclotrons
Spiral 1 beam
SPIRAL2 LINAC
S3-LEB beam
HRS
RFQ-1P
Courtesy: C. Berteloite, GANIL
14

## Slide 15
Beam preparation and purification
DESIR

## Slide 16: Beam preparation and purification
HRS
MR-ToF
Clean most of isobars
Clean almost all isobars
Clean isomeric states separated by a few 10 keV
Trap-assisted spectroscopy
s
s
s
PIPERADE
1st trap
PIPERADE
2nd trap
Time vs Resolving power
Beam preparation:
- Cooling and bunching
- Accumulation trap
Mass separation/beam purification:
GPIB
Mass measurements:
Mass precision: 10-8 – 10-9
MR-ToF
RFQ-Cooler Buncher
BRIoCHe
Double Penning Trap
RFQ Cooler
High Resolution Separator HRS
MR-ToF-MS
TRAMWAY
PIPERADE
Courtesy: B. Blank, C. Berteloite
s
16

## Slide 17: Beam preparation and purification: RFQ cooler
Quadrupole triplet
Diagnostics
Ion source
RFQ
RFQ1P test bench at LPC Caen (w/o the HV cage)
Construction and tests at LPC Caen
- technical commissioning: end-2026
- offline commissioning: early 2027
-> transfer to GANIL: mid-2027
RF circuit
HV cage
Quadrupole
Based on the SHIRAC RFQ studied within SPIRAL2-Phase 2 and an upgraded version for SPES
R. Boussaid et al., JINST 9 (2014) P07009
Material: J.-F. Cam, LPC Caen
17

## Slide 18: Beam preparation and purification: HRS
Fully commissioned at LP2iB - J. Michaud, A. Balana, B. Blank, L. Daudin
-> transfer to GANIL: end-2026
J. Michaud et al., NIM B 541, 161 (2023)
T. Kurtukian Nieto et al., NIM B 317, 283 (2013)
HRS
PIPERADE
BRIoCHe
18

## Slide 19
Timeline
DESIR

## Slide 20: Tentative timeline (preliminary)
20
Demonstrator
Commissioning: March 27
RFQ-1P + HRS
Installation: Dec. 27
BRIoCHe + PIPERADE
Installation: Sept 27 -> June 28
Transport beam lines
Installation: Dec. 27
RIB in Exp. hall
Sept. 29?
SIB before Exp. hall
Feb. 29?

## Slide 21: Tentative timeline (preliminary)
21
Tentative planning (DESIR COPIL and CAF – Oct.-Nov. 2026)
-> To be consolidated

## Slide 22
Conclusion
DESIR

## Slide 23: Conclusion
Critical points
Stable ion source for experimental equipment commissioning
1st laser room operation
Upgrade of the maximal Br value of SPIRAL1 RIBs
Transfer of technical developments to the GANIL staff
23

## Slide 24
Thanks for your attention
NEWGAIN