## Sheet1
|  |  | SuperBeams | [9 empty] | Generated : | 2011-05-25 12:55
cmd (n,m,d) | Code | New Code* | Name* | Multiplicity* | Date Of Estimate | Tech. Uncertainty | Expected Offers | Type | Unit | Industrial Index | Technical Responsible | Technical Expert | External link | Comments
| ROOT | ROOT | Cern2Frejus | 1
| 1. | 1. | SPL Proton Driver | 1 | [6 empty] | Garoby
| 2 | 2 | Infrastructure & services | [7 empty] | ?
| 2.1 | 2.1 | Civil Engineering | [7 empty] | ?
| 2.1.1 | 2.1.1 | CE work for SPL
| 2.1.2 | 2.1.2 | CE work for accumulator
| 2.1.3 | 2.1.3 | CE work for beam splitter/transport
| 2.1.4 | 2.1.4 | CE work for target station
| 2.1.4.1 | 2.1.4.1 | Target Hall | 1
| 2.1.4.2 | 2.1.4.2 | Target services hall/tunnel | 1
| 2.1.4.3 | 2.1.4.3 | Target Hall access shaft | 1
| 2.1.4.4 | 2.1.4.4 | Target Hall surface building | 1
| 2.1.5 | 2.1.5 | CE work for Decay Volume
| 2.1.6 | 2.1.6 | CE work for hadron absorber/muon pit
| 2.1.6.1 | 2.1.6.1 | Dump pit | 1
| 2.1.6.2 | 2.1.6.2 | Dump/mu monitors surface building | 1
| 2.1.7 | 2.1.7 | CE work for near detector
| 2.1.7.1 | 2.1.7.1 | ND access shaft | 1
| 2.1.7.2 | 2.1.7.2 | ND hall | 1
| 2.1.7.3 | 2.1.7.3 | ND surface building | 1
| 2.1.8 | 2.1.8 | Global services buildings | 1
| 2.2 | 2.2 | Power | [10 empty] | a test
| 2.2.1 | 2.2.1 | Cabling
| 2.3 | 2.3 | Access & communications
| 2.4 | 2.4 | Cooling fluids
| 2.4.1 | 2.4.1 | Primary (active) water cooling plant
| 2.4.1.1 | 2.4.1.1 | TS shield cooling | 1
| 2.4.1.2 | 2.4.1.2 | DV cooling | 1
| 2.4.1.3 | 2.4.1.3 | Beam dump cooling | 1
| 2.4.1.4 | 2.4.1.4 | Target cooling circuit | 1
| 2.4.1.5 | 2.4.1.5 | Baffle cooling circuit
| 2.4.2 | 2.4.2 | Secondary (cooling tower) water plant | 1
| 2.5 | 2.5 | Ventilation
| 2.5.1 | 2.5.1 | Active ventilation systems
| 2.5.1.1 | 2.5.1.1 | Ventilation: TS helium vessel
| 2.5.1.2 | 2.5.1.2 | Ventilation: TS environment
| 2.5.1.3 | 2.5.1.3 | Ventilation: TS inner shield
| 2.5.1.4 | 2.5.1.4 | Ventilation: TS Hot cell
| 2.5.1.5 | 2.5.1.5 | Ventilation: DV shield
| 2.5.1.6 | 2.5.1.6 | Ventialtion: Beam dump/mupit
| 2.6 | 2.6 | Transport and Installation
| 2.7 | 2.7 | Health & Safety
| 2.8 | 2.8 | Survey & alignment
| 2.9 | 2.9 | Machine Operation (/ controls/interlocks?)
| 2.1 | 2.1 | Fixed shielding
| 3 | 3 | Accumulator | 1 | [6 empty] | Dracos?
| 4 | 4 | Beam splitter & transport | 1 | [6 empty] | Dracos?
| 5 | 5 | Target Station | 1 | [6 empty] | Densham
| 5.1 | 5.1 | Mobile shielding
| 5.2 | 5.2 | Target station vessel
| 5.3 | 5.3 | Beam window module
| 5.3.1 | 5.3.1 | Beam window
| 5.3.2 | 5.3.2 | Beam window helium cooling plant
| 5.3.3 | 5.3.3 | Beam window support + shielding
| 5.4 | 5.4 | Baffle/collimator module
| 5.4.1 | 5.4.1 | Baffle support module
| 5.4.2 | 5.4.2 | Baffle
| 5.5 | 5.5 | Target and horn module
| 5.5.1 | 5.5.1 | Support module + strip lines | 1
| 5.5.2 | 5.5.2 | Targets + target supports | 1
| 5.5.3 | 5.5.3 | Horn assemblies | 4
| 5.5.4 | 5.5.4 | Target & horn instrumentation
| 5.6 | 5.6 | Horn power supplies | 4
| 5.6.1 | 5.6.1 | PSU controls
| 5.7 | 5.7 | Helium cooling plant | 1
| 5.8 | 5.8 | Remote handling cell | 1
| 5.8.1 | 5.8.1 | Shielding window | 1
| 5.8.2 | 5.8.2 | Manipulators | 2
| 5.8.4 | 5.8.4 | Remote handling equipment
| 5.8.5 | 5.8.5 | Fitting out
| 5.8.6 | 5.8.6 | Steel liner
| 5.9 | 5.9 | Cranes, lifting, handling equipment
| 5.9.1 | 5.9.1 | Cranes | 2
| 5.9.2 | 5.9.2 | Lift tables
| 5.9.3 | 5.9.3 | Lifting equipment
| 5.9.4 | 5.9.4 | Supports, fixtures
| 5.9.5 | 5.9.5 | Shielded flasks
| 5.1 | 5.1 | TS controls/instrumentation
| 5.11 | 5.11 | Vacuum and helium equipment
| 5.11.1 | 5.11.1 | Vacuum pumps and controllers
| 5.11.2 | 5.11.2 | TS helium plant
| 5.11.2.1 | 5.11.2.1 | Helium pumps and controllers
| 5.11.2.2 | 5.11.2.2 | helium tanks
| 5.12 | 5.12 | Morgue
| 5.13 | 5.13 | TS fitting out
| 6 | 6 | Decay pipe
| 7 | 7 | Hadron absorber + muon monitor | 1
| 7.1 | 7.1 | Absorber core
| 7.2 | 7.2 | Absorber shielding
| 7.3 | 7.3 | Absorber instrumentation
| 8 | 8 | Near Detector | 1
| 9 | 9 | Far Detector | 1 |  |  |  | Tracking