## Sheet1
Latest modification = |  | 2008-07-15 |  | by |  | Pasquale, Federico
Components needed for 1st EU SM | Institution | Contact | Drawing | Drawing Status | SM Fraction | Components Amount | Requested Companies | Chosen Company | Delivery | Cost | Comment
DRAWING CODES
Lead Tiles | LNF | Bianchi | 26K204_C | prod | 0.77845 | 16416 | Goslar(2.69)/Lemer(3.45)/Cecom(3.55) | Goslar | 96 blocks Aug 10, Sept 15 120 blocks, Oct-15 remaining 72 blocks | 42k | Next batch should be production
Lead Tool | LNF | Bianchi |  |  |  | 1 | Goslar/Lemer/Cecom | Goslar | April | 11k
Scintillator Tiles | LNF | Di Nezza | 26K205A | prod | 1 | 88704 | Uniplast |  | 20000 pcs July - August [?] | 12k | dim. Check ok
Scintillator mould | LNF | Di Nezza |  |  |  | 1 | Uniplast |  | April | 5k | US vs EU mould
Cut & paint for scintillators | LNF | Ronchetti | 26K205A |  | 1 | 88704 | Lceram (GeneralTecnica,Cecom,B3,Meccanotecnica) | Lceram | Fresh tiles tested | 17k | Tooling commissioned
Bond Paper | LNF | Dinezza, Hasch | 26K206_B | prod | 3 | 133056 | WSU (3M,Fabriano,NANTES) German Companies | KRICK (Germany) SOUTHWORTH PAPER | Jul 10, delivered for processing, final Aug 10 | 15K | LASER CUT AND HOLES 4 basic sizes (0.035 E/sheet + 3KE Tool) - waiting for final quote.(correct 2x76 layers --> 2x77)
Front Plate | LNF | Ronchetti | 26K200J | prod | 1.125 | 324 | Meccanotecnica,B3,Generaltenica,Cecom | Meccanotec. | 2008-06-18 | 6k | 144 - 1.3 mm drills (regular) + chamfer
Compression Plate | LNF | Ronchetti | 26K202F | prod | 1.125 | 324 | Meccanotecnica,B3,Generaltenica,Cecom | Meccanotec. | 2008-06-18 | 6k | 144 - 1.3 mm drills (regular) + chamfer
Back Plate | LNF | Ronchetti | 26K201I | prod | 1.125 | 324 | Meccanotecnica,B3,Generaltenica,Cecom | Meccanotec. | 2008-06-18 | 8k | 144 - 1.3 mm drills (regular) + chamfer
Modified piston/plunger | LNF | Ronchetti | 26K201I | prod | N/A | 60 | Meccanotec. | Meccanotec. | mid-aug | 0 | to fix BP OPQRS error
Side Straps foil | INFN | Dialinas | 26K214C | prod | 1 | 1152 | LPSC, SUBA |  |  |  | (7E foil(3SM)+flange+tooling)
Side Strap Flange | INFN | Dialinas | 26K208H |  | 3 | 3456
Side Straps welding | INFN | Di Nezza / Dialinas | 26K203E |  | 0.86806 | 1000 | LR-LPSC | LRA | end of july |  | laser welding 7Euro x welding
M2.5 Screws for Straps | LNF | Ronchetti | in stock |  | 3 | 20736 |  |  | end of july |  | underway
Side black paper | LNF | Ronchetti | in stock |  | 3 | 864 | 3M,WSU, (SONY mod. PET 7586-25) | Sony | 1 rool Delivered, 2nd to be odrered |  | delivered in rolls to be cut
Mask for black paper cut | LNF | Ronchetti | 26K211B (half,full) |  | 3 | 2 | ISOLCERAM | ISOLCERAM | underway |  | cut for 3 EU SM
WLS fiber | LNF | Di Nezza |  |  | 1.3105 | 25 | Kuraray |  | Delivered | 40k | for 1.5 SM L=367 mm (US: ordered for all the US SMs)
Fiber Bundle Terminator | LNF | Di Nezza, Ronchetti | 26K207D |  | 3 | 3456 | Lceram, LMP(Amicuzzi), CECOM (WSU for everybody. | WSU | 2008-07-18 |  | delayed
APD Mount | LNF | Di Nezza, Ronchetti | 26K309C |  | 3 | 3456 | Lceram, LMP(Amicuzzi), CECOM (WSU for everybody. Waiting for an offer) | WSU | 2008-07-18 |  | delayed
APD manifold | LNF | Di Nezza, Ronchetti | 26K307B |  | 3 | 3456 | Lceram, LMP(Amicuzzi), CECOM (WSU for everybody. Waiting for an offer) | WSU | 2008-07-18 |  | delayed
Light guide | LNF | WSU | 26K308A |  | 1 | 1152 | Uniplast | WSU | ?? |  | problem with US transaction (exchange w/ belleville washers)
Belleville washers | LNF | Ronchetti | 800 |  | 5.2083 | 7500 | Schnorr |  | end of august | 13.5k | (ordered) packed
Plunger Pin | LNF | Ronchetti,Noto | 26K209D | APPROVED | 1.088 | 4700 | Meccanotecnica, B3, CECOM |  | MT (0.77E), delivery: mid-aug | 3760 | 0.54 E/piece machined Stainless steel(corea .35$/piece brass)
M6 screw for load set | LNF | Ronchetti | in stock |  | 1.0417 | 4500 |  |  | end of july |  | underway
Ø8 Dowel pin | LNF | Ronchetti | 26K214_A |  |  | 1152 | in stock
Ø8/10 DUB dry bearing | LNF | Ronchetti | not need | Appr. |  | 1152 | GGB |  |  |  | 08212DUB
M5 studs | SUB | Dialinas | 26K212A | APPROVED | 3 | 3456 | Meccanotecnica, B3, CECOM |  | B3 (2.05 /pcs) | 8k | underway
M5 nuts and washers | LNF | Ronchetti | in stock |  | 1 | 1152 |  |  | end of july
APD | CT | Badala` | in stock |  | 1 | 1152 | hamamatsu/cern |  | september |  | INFN order (37 E/each)
Preampl | SUB | Roy |  |  | 1 | 1152 | PHOS supplier |  | August [?] |  | order with US
Calibration LED | WSU | Cormier, Pompei |  |  |  |  | WSU |  |  |  | Halogen free ?
Ferrule for Cal. LED | WSU | Cormier, Pompei |  |  | 1 | 288 | WSU |  | 15/6/2008
Strongback | SUB | Dialinas | Rev.A |  | 1 | 24 | SUBA |  | June
Cover Plate | SUB | Dialinas | drawing ! |  | 1 | 72 | Inquiry ! |  |  |  | 5 (3+2) pieces per Strip
Screws for Cover Plate | SUB | Dialinas | in stock
clips for R.O. cables | SUB | Dialinas
T-cards | CERN | Awes | [6 empty] | end of july |  | 4 weeks delivery
stud for T-card fixation to SB | SUB | Dialinas | drawing ! |  |  |  | Inquiry !
Screws for T-card fixation to T card | SUB | Dialinas | in stock
Fixations for T-Cards | SUB | Dialinas | drawing ! |  |  |  | Inquiry ! |  |  |  | 4 weeks delivery (1.5 E/part)
Molex Cables and Connectors | CERN | Awes |  |  |  | 60000 | CERN/phos |  | end of july |  | cables+connectors (1.35 E/piece)
Read-Out cables and connectors | CERN | Awes |  |  | 1 | 24 |  |  | end of july |  | custom cut for 1st module
M16 Screws for fixing the SB on the SM | SUB | Dialinas | 2 x C HC screws, M10-40, Stainless steel A2-70 4 x C HC screws, M10-35, Stainless steel A2-70
SM cradle (crate) | CT, LNF | Palmeri, Di Nezza | drawing released (put link) |  | 1 | 1 |  | B3 | june | 12k +36k | 4 orderd (+ proto) check if bars are included in the order
Electronic crate | CERN | Awes | complete |  | 1 | 1 |  |  |  | ? | 2month drawing,1 month fabrication
O-rings for FT | LNF | Ronchetti | in stock |  | 1.0417 | 1200
O-rings for APD | LNF | Ronchetti | in stock |  | 1.0417 | 1200
Spring clip | LNF | Ronchetti | drawing ! |  | 1.0417 | 1200